## Prioritized Roadmap
Phase | Timeline | Feature | Description | Priority | Effort (Weeks) | Dependencies
Phase 1: MVP | Months 0-6 | Building input workflow | Step-by-step form for dimensions, materials, location | P0 | 4 | None
Phase 1: MVP | Months 0-6 | Material database | CIBSE/ASHRAE defaults + custom entry | P0 | 2 | None
Phase 1: MVP | Months 0-6 | Climate data integration | OpenWeatherMap/Meteonorm API | P0 | 2 | None
Phase 1: MVP | Months 0-6 | Heat loss calculation | BS EN 12831 simplified | P0 | 2 | Materials DB
Phase 1: MVP | Months 0-6 | Heat pump sizing | Capacity + model selection | P0 | 2 | Climate DB
Phase 1: MVP | Months 0-6 | COP/SCOP estimation | Linear model vs. temperature | P0 | 1 | Climate DB
Phase 1: MVP | Months 0-6 | Basic economics | CAPEX, OPEX, payback, carbon savings | P0 | 2 | Economic DB
Phase 1: MVP | Months 0-6 | Results dashboard | Charts, summary, export PDF | P0 | 3 | All above
Phase 2: Expansion | Months 6-12 | Greenhouse input mode | Crop type, growing area, glazing | P0 | 4 | MVP
Phase 2: Expansion | Months 6-12 | Plant database | Optimal temp/humidity for 50+ crops | P0 | 2 | None
Phase 2: Expansion | Months 6-12 | Greenhouse heat loss model | Different from buildings (glazing, ventilation) | P0 | 3 | Plant DB
Phase 2: Expansion | Months 6-12 | Hybrid systems | Solar + heat pump + storage | P1 | 4 | MVP
Phase 2: Expansion | Months 6-12 | Advanced economics | NPV, IRR, local incentives | P1 | 3 | Economic DB
Phase 2: Expansion | Months 6-12 | Dynamic simulation | Hourly/transient analysis | P1 | 6 | MVP

## Summary
Phase | Timeline | Focus | Key Deliverables
Phase 1 MVP | Months 0-6 | Buildings-only feasibility | Web app, core calculations, basic DB
Phase 2 Expansion | Months 6-12 | Greenhouses + Advanced Features | CEA mode, hybrid systems, incentives
Phase 3 Monetization | Months 12-18 | Revenue Generation | Freemium, subscriptions, API
Phase 4 Enterprise | Months 18-24 | Scaling & Customization | Team features, BIM integration, white-label

## Phase 3 Monetization
Phase | Timeline | Feature | Description | Priority | Effort (Weeks) | Dependencies
Phase 3 Monetization | Months 12-18 | Freemium model | Free tier + paid upgrades | P0 | 2 | None
Phase 3 Monetization | Months 12-18 | Subscription plans | Pro ($20/mo), Business ($100/mo) | P0 | 2 | Stripe integration
Phase 3 Monetization | Months 12-18 | Pay-per-report | One-time detailed reports | P0 | 1 | PDF generation
Phase 3 Monetization | Months 12-18 | API access | For integrations (paid) | P1 | 4 | Swagger docs
Phase 3 Monetization | Months 12-18 | Team collaboration | Shared projects, comments | P1 | 3 | MVP

## Phase 4 Enterprise
Phase | Timeline | Feature | Description | Priority | Effort (Weeks) | Dependencies
Phase 4 Enterprise | Months 18-24 | BIM/Revit integration | Import building models | P0 | 6 | MVP
Phase 4 Enterprise | Months 18-24 | On-premise deployment | Self-hosted option | P0 | 4 | On-premise
Phase 4 Enterprise | Months 18-24 | Custom databases | Client-specific materials/heat pumps | P1 | 3 | Custom databases
Phase 4 Enterprise | Months 18-24 | Advanced reporting | White-paper-quality PDFs | P2 | 3 | PDF templates